## Legend
Risk Register: How to Use This Workbook
Formula-driven register built from ITGC testing, a vulnerability assessment and an enterprise risk list
Sheets
Register | One row per risk. Edit the blue cells. Scores, ratings, flags and rank are formulas.
Heat Map | 5x5 likelihood and impact grids (inherent and residual) with live risk counts per cell.
Summary | Counts by rating, status, source and category, plus the top 5 risks and a chart.
Scale | Rating thresholds, report as-of date, and the 1-5 likelihood and impact definitions.
Cell colour key
Blue text | Input. Safe to change.
Black text | Formula. Do not overwrite.
To add a risk | Copy the last filled row on Register down one row (formulas included) and edit the blue cells. Formulas on Heat Map and Summary read rows 5 to 54 of Register.
To change the rating bands | Edit the minimum scores on Scale (B5:B8). Ratings and heat map colours update.
To change the as-of date | Edit Scale!B11. Days to Target and the OVERDUE flag update. Use =TODAY() there for a live view.
Assumptions
Scoring | Score = likelihood x impact, each 1 to 5, giving 1 to 25. Same bands as the risk-register-tracker repo.
Inherent vs residual | Inherent = before the planned mitigation. Residual = after it is fully in place (a target, not a measurement).
Sources | R-01 to R-04 come from the itgc-controls-testing repo. R-05 to R-08 come from the vulnerability-assessment-report repo. R-09 to R-15 are the enterprise risks from the risk-register-tracker repo.
Rescaling | The vulnerability assessment scored on a 1 to 3 scale. Those risks are rescored here on 1 to 5; the original scores are recorded in each description. The new scores are my judgment, not measured data.
Data | All data is synthetic and for portfolio demonstration. Dates and owners are illustrative.

## Register
Risk Register
Blue cells are inputs; black cells are formulas. Rows 5 to 54 feed the other sheets.
Risk ID | Risk Title | Category | Source | Description | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Risk Owner | Treatment | Mitigation / Response | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Risk Reduction | Status | Target Date | Days to Target | Overdue? | Rank Key (helper)
R-01 | Terminated users retain active ERP access | Access Control | ITGC Testing | Control 1 test: U1003 (terminated 2026-05-15) and U1010 (terminated 2026-06-02) were still Active in the finance ERP at the 2026-06-15 audit date. | 4 | 4 | 16 | Critical | IT Security | Mitigate | Disable both accounts now; trigger deprovisioning from HR termination events; reconcile HR terminations to active accounts monthly. | 1 | 4 | 4 | Low | 75% | In Progress | 2026-10-15 | -15 | OVERDUE | 16.0099
R-02 | Periodic access reviews overdue | Access Control | ITGC Testing | Control 2 test: U1010 (last review 2025-11-01) and U1016 (2025-09-01) are past the six-month review cycle. | 3 | 3 | 9 | Medium | Finance Controller | Mitigate | Complete the overdue reviews; calendar semi-annual recertification with manager sign-off tracked to completion. | 1 | 3 | 3 | Low | 66.67% | In Progress | 2026-11-30 | 31 |  | 9.0099
R-03 | Production changes without independent approval | Change Management | ITGC Testing | Control 3 test: CH-2203 and CH-2207 had no approver; CH-2206 was approved (2026-05-18) after it was implemented (2026-05-14); CH-2208 was self-approved. | 4 | 4 | 16 | Critical | IT Infrastructure | Mitigate | Block deployment in the ticketing system until an independent approval is logged; prevent requester from approving own change; review the four changes after the fact. | 2 | 4 | 8 | Medium | 50% | Open | 2026-12-15 | 46 |  | 16.0099
R-04 | AP and Purchasing roles held by one user | Segregation of Duties | ITGC Testing | Control 4 test: U1016 holds AP Clerk and Purchasing Agent, so one person can create a purchase order and process its payment. | 3 | 4 | 12 | High | Finance Controller | Mitigate | Remove the Purchasing Agent role, or add supervisor review of all payments this user processes until it is removed. | 1 | 4 | 4 | Low | 66.67% | Open | 2026-11-15 | 16 |  | 12.0099
R-05 | Customer database reachable from the public internet | Network Security | Vulnerability Assessment | The customer database server has accepted connections from any public address since launch. Assessment scored data exfiltration 3x3 on a 1-3 scale; rescored 4x5 here. | 4 | 5 | 20 | Critical | IT Infrastructure | Mitigate | Restrict inbound access to an allow-list of office and VPN egress addresses; require MFA for administrative access. | 1 | 5 | 5 | Medium | 75% | Open | 2026-12-31 | 62 |  | 20.0099
R-06 | Automated scanners find the exposed database | Network Security | Vulnerability Assessment | Public database ports are scanned continuously and can become a foothold for further attacks. Assessment scored 3x2; rescored 5x3 here. | 5 | 3 | 15 | Critical | IT Infrastructure | Mitigate | Same allow-list as R-05; alert on connection attempts from outside the allow-list. | 1 | 3 | 3 | Low | 80% | Open | 2026-12-31 | 62 |  | 15.0099
R-07 | Employee alters or deletes customer records | Data Protection | Vulnerability Assessment | A malicious or careless employee changes or deletes records, disrupting sales operations. Assessment scored 2x2; rescored 2x3 here. | 2 | 3 | 6 | Medium | IT Security | Mitigate | Role-based access with read-only query access for sales staff; audit logging on write operations. | 1 | 3 | 3 | Low | 50% | Open | 2027-01-31 | 93 |  | 6.0099
R-08 | Database connections use deprecated SSL | Data Protection | Vulnerability Assessment | The assessment recommended moving from SSL to TLS 1.2 or higher on all permitted connections because SSL has known weaknesses. | 3 | 3 | 9 | Medium | IT Infrastructure | Mitigate | Disable SSL, enforce TLS 1.2 or higher, and confirm with a configuration scan. | 1 | 3 | 3 | Low | 66.67% | Open | 2026-12-15 | 46 |  | 9.0099
R-09 | Unpatched ERP server vulnerability | Vulnerability Management | Enterprise Register | Critical CVE identified on the production ERP application server; no patch applied yet. | 4 | 5 | 20 | Critical | IT Infrastructure | Mitigate | Apply the vendor patch in the next maintenance window; add a compensating WAF rule in the interim. | 2 | 5 | 10 | High | 50% | In Progress | 2026-11-20 | 21 |  | 20.0099
R-10 | No MFA on remote VPN access | Access Control | Enterprise Register | Remote access to the internal network does not require multi-factor authentication. | 3 | 5 | 15 | Critical | IT Security | Mitigate | Roll out MFA enforcement for all VPN users. | 1 | 5 | 5 | Medium | 66.67% | Open | 2026-12-01 | 32 |  | 15.0099
R-11 | No tested ransomware response runbook | Incident Response | Enterprise Register | The organization has no documented, tested runbook for a ransomware scenario. | 3 | 5 | 15 | Critical | IT Security | Mitigate | Draft the runbook and run a tabletop exercise to test it. | 2 | 5 | 10 | High | 33.33% | Open | 2027-01-15 | 77 |  | 15.0099
R-12 | Shared admin credentials on legacy file server | Access Control | Enterprise Register | A legacy file server uses one shared administrator account instead of individual accounts. | 4 | 3 | 12 | High | IT Infrastructure | Mitigate | Migrate to individual admin accounts with logging enabled. | 1 | 3 | 3 | Low | 75% | Open | 2026-11-30 | 31 |  | 12.0098
R-13 | Backup restoration untested for over a year | Business Continuity | Enterprise Register | The restoration procedure for the financial database had not been tested in over a year. | 2 | 5 | 10 | High | IT Infrastructure | Mitigate | Run and document a full restoration test. | 1 | 5 | 5 | Medium | 50% | Closed | 2026-10-01 |  |  | 10.0098
R-14 | Payroll data in unencrypted spreadsheets | Data Protection | Enterprise Register | Payroll data was found in unencrypted spreadsheets on a shared drive. | 3 | 4 | 12 | High | Finance Controller | Mitigate | Move the data to an access-controlled system and encrypt existing files. | 1 | 4 | 4 | Low | 66.67% | Open | 2026-12-10 | 41 |  | 12.0098
R-15 | Critical vendor risk assessments out of date | Third-Party Risk | Enterprise Register | Several critical vendors have not been reassessed in over 18 months. | 3 | 3 | 9 | Medium | Procurement | Mitigate | Reassess all critical vendors now and move to a 12-month cycle. | 2 | 3 | 6 | Medium | 33.33% | Open | 2027-02-01 | 94 |  | 9.0098

## Heat Map
Risk Heat Maps
Each cell counts the risks at that likelihood and impact. Colour = rating band for that cell.
Inherent risk (before mitigation)
Likelihood
|  | 1 | 2 | 3 | 4 | 5
Impact | 5 | 0 | 1 | 2 | 2 | 0
| 4 | 0 | 0 | 2 | 2 | 0
| 3 | 0 | 1 | 3 | 1 | 1
| 2 | 0 | 0 | 0 | 0 | 0
| 1 | 0 | 0 | 0 | 0 | 0
| Total | 15
Residual risk (after planned mitigation)
Likelihood
|  | 1 | 2 | 3 | 4 | 5
Impact | 5 | 3 | 2 | 0 | 0 | 0
| 4 | 3 | 1 | 0 | 0 | 0
| 3 | 5 | 1 | 0 | 0 | 0
| 2 | 0 | 0 | 0 | 0 | 0
| 1 | 0 | 0 | 0 | 0 | 0
| Total | 15

## Summary
Risk Summary
All figures are formulas over the Register sheet.
Risks by rating |  |  |  | Key figures
Rating | Inherent | Residual |  | Average inherent score |  | 13.0667
Critical | 7 | 0 |  | Average residual score |  | 5.0667
High | 4 | 2 |  | Average risk reduction |  | 60.33%
Medium | 4 | 5 |  | Open or in-progress risks |  | 14
Low | 0 | 8 |  | Overdue mitigations |  | 1
Total | 15 | 15
Risks by status |  |  |  | Risks by source
Status | Count |  |  | Source |  | Count
Open | 11 |  |  | ITGC Testing |  | 4
In Progress | 3 |  |  | Vulnerability Assessment |  | 4
Closed | 1 |  |  | Enterprise Register |  | 7
Risks by category
Category | Count | Total inherent score
Access Control | 4 | 52
Change Management | 1 | 16
Segregation of Duties | 1 | 12
Network Security | 2 | 35
Data Protection | 3 | 27
Vulnerability Management | 1 | 20
Incident Response | 1 | 15
Business Continuity | 1 | 10
Third-Party Risk | 1 | 9
Total | 15 | 196
Top 5 risks by inherent score
Rank | Risk ID | Title | Inherent | Rating | Residual | Owner | Status
1 | R-05 | Customer database reachable from the public internet | 20 | Critical | 5 | IT Infrastructure | Open
2 | R-09 | Unpatched ERP server vulnerability | 20 | Critical | 10 | IT Infrastructure | In Progress
3 | R-01 | Terminated users retain active ERP access | 16 | Critical | 4 | IT Security | In Progress
4 | R-03 | Production changes without independent approval | 16 | Critical | 8 | IT Infrastructure | Open
5 | R-06 | Automated scanners find the exposed database | 15 | Critical | 3 | IT Infrastructure | Open

## Scale
Scoring Scale and Settings
Rating | Min score | Meaning
Low | 1 | Accept or monitor
Medium | 5 | Mitigate within the planning cycle
High | 10 | Mitigate with an owner and a dated plan
Critical | 15 | Escalate to management; mitigate first
Settings
Report as-of date | 2026-10-30 | Input. Fixed so results are reproducible; replace with =TODAY() for a live view.
Likelihood | Level | Definition
1 | Rare | Not expected in the next 12 months
2 | Unlikely | Could occur, but no recent indicators
3 | Possible | Has occurred in similar organizations or shows some indicators
4 | Likely | Weakness is confirmed and exploitable with little effort
5 | Almost certain | Exposed now or already occurring
Impact | Level | Definition
1 | Minimal | Negligible cost or disruption
2 | Minor | Limited disruption, absorbed in normal operations
3 | Moderate | Noticeable disruption or loss of one function or dataset
4 | Major | Financial reporting error, data breach or audit finding
5 | Severe | Material misstatement, large breach or extended outage